## Sheet1
Task Name | Description | Status
Sprint 1
Task 1 | Setup a 2D Environment in Unreal | Complete
Task 2 | Move Assests From Unity to Unreal | Complete
Task 3 | Convert Textures to Sprites and Organize to into Folders | Complete
Task 4 | Rough outline home screen and first level screen | Complete
Task 5 | Scale backgrounds in Unreal | In Progress
Task 6 | Separate screens into different levels | Complete
Task 7 | Implement Click play button transition from first level to second level | Complete
Task 8 | Make the images animated were they are popping up on game load | Complete
Task 9 | Add sound as they are popping up | Complete
Task 10 | Adjust spacing on the home screen | In Progress
Sprint 2
Task 1 | Fix Camera | In Progress
Task 2 | Mouse over 'New Game' / 'Continue' Color Change | In Progress
Task 3 | Information Button | In Progress
Task 4 | Blinking Cell Animations | In Progress
Task 5 | Link Menu to Appropriate Cell Screen | In Progress
Task 6 | Begin Work on the Cell Screen | In Progress
Task 7 | Add tutorial that shows how to play the game, make moves in the game, change background color, etc. | In Progress